MATERIAL REQUISITION MANAGEMENT PROCEDURE

TABLE OF CONTENT

1.	INTRODUCTION	3

2.	MATERIAL REQUISITION MANAGEMENT PROCEDURE	4

INTRODUCTION

...

MATERIAL REQUISITION MANAGEMENT PROCEDURE

Material requisition management is summarized as outlined here below.

| Step | Phase | Executor | Action | Documentation |
| --- | --- | --- | --- | --- |
|  | Request for quotation | Engineering | - Preparation of the Material Requisition for Quotation and relevant attachments. - Forwarding of Material Requisition to Project Manager. | - MR for RFQ |
|  | Request for quotation | Project Manager | - Preparation of the request for quotation. - Forwarding of material requisition and request for quotation to Purchasing dept. | - MR for RFQ |
|  | Request for quotation | Purchasing dept. | - Sending of Request for Quotation to vendors. (email da portale al fornitore con allegati) - MR + Allegati | - |
|  | Quotation collected | Purchasing dept. | - Receiving of quotation from vendors. - Forwarding of vendors’ quotation to Engineering dept. for alignement. - (alert ad ogni caricamento) | - Vendors’ quotation |
|  | Quotations alignement | Engineering | - Technical alignment of received quotations. - Technical tabulation of received quotations. - Preparation of BTA (Bid Technical Alignment sheet) and BTE (Bid Technical Evaluation sheet) (1). - Sending of aligned and tabulated quotations (TBA and TBE sheets) to Project Manager. | - BTA (Bid Technical Alignment sheet) - BTE (Bid Technical Evaluation sheet) |
|  | Quotations tabulation | Project Manager | - Evaluation of TBE sheet. - Sending of tabulated quotations (PM’s TBE sheet) to Purchasing dept. | - TBE sheet |
|  | Quotations tabulation | Purchasing dept. | - Negotiation with acceptable vendors. - Selection of vendor. - Information to Engineering dept. of selected vendor. | - (to be defined) |
|  | Quotations tabulation | Engineering | - Preparation of the Material Requisition for Order and relevant attachments, including TBA relevant to selected vendor. - Forwarding of Material Requisition for Order to Project Manager. | - MR for PO |
|  | Request for purchase | Project Manager | - Preparation of the Request for Order. - Forwarding of Material Requisition and Request for Order to Purchasing dept. | - MR for PO - RFO |
|  | Order | Purchasing dept. | - Release of purchase order | - Order |

Notes:

- In case during technical alignement vendor’s quotations shall be revised/amended, new quotation or amendments shall be included in the technical alignement and tabulation.